## Slide 1
Every module tested end-to-end · canary window = 2.5wk (Internal 1wk + Pilot 1.5wk)
Oct '26
Prerequisites
Nov–Dec '26
DST Gates
Jan '27
Feb '27
Mar '27
Apr '27
1. Password Reset
Runs in parallel with Solution → MyPassword
2. Solution (Solutions + Context)
Runs in parallel with Password Reset → no legacy app to retire
3. Accounts
Starts once Solution clears its pilot gate → retires MyAccount
4. Groups
No legacy app to retire
5. Access Control
Depends on validated Groups data → hard floor: 3wk pilot-to-ramp → retires MyAccess
5
Prerequisites cleared
6
DST gates to clear
⚑ Prerequisite complete
◇ Pilot clear
Internal 1%
Pilot ◇ → Ramp 25/50/75/100%
✓ 100% – 7wk mark
◇ Pilot clear → starts Accounts
Internal 1%
Pilot ◇ → Ramp 25/50/75/100%
✓ 100% – 7wk mark
◇ Pilot clear → starts Groups
Internal 1%
Pilot ◇ → Ramp 25/50/75/100%
✓ 100% – 9wk mark
◇ Pilot clear → starts Access
Internal 1%
Pilot ◇ → Ramp 25/50/75/100%
✓ 100%
Internal 1%
Notes: Prerequisites cleared (5): include Security & Infra Review, Quality & Eco Design, Data Officer Validation (add the remaining two). DST gates to clear (6 key reports): include UX & Performance, Automation & Code Quality, Chemarx & LPAC Roles (add the remaining three).